## Sheet1
Sprint 1 Backlog
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
3 | As an admin, I want to download reports about books, transactions, and other business data in CSV format, so I can conduct stock-take and complete accounting forms. | 1.1 |  |  |  |  | x | DODs Complete
|  | 1.2 | Integrate CSV with backend | Mohammed
7 | As an admin user, I want to view a summary of all past and current transactions (sorted by date), so I can keep track of business profits. | 2.1 |  |  |  |  | x | DODs Complete
|  | 2.2 | Transactions Microservice : get transactions | Allister
|  | 2.3 | Display all transactions | Mohammed
11 | As a public user, I want to review books that I have purchased, so I can give my thoughts and opinions on that book. | 4.1 |  |  |  |  | x | DODs Complete
|  | 4.2 | Reviews Microservice : add reviews, get reviews | Ross
|  | 4.3 | Add + display reviews | Jeffrey
12 | As a business owner, I want to create listings for my books, so that other users can purchase those items. | 6.1 |  |  |  |  | x | DODs Complete
|  | 6.2 | Listings Microservice | Ross
|  | 6.3 | Add listing form | Mohammed
13 | As a public user, I want to create share listings for my books, so that I can provide others with books I don't need. | 8.1 |  |  |  |  | x | DODs Complete
|  | 8.3 | Add listing form | Mohammed
14 | As a public user, I want to pay for transactions using PayPal, so I can have the book delivered to me. | 9.1 |  |  |  |  | x | DODs Complete
|  | 9.2 | Transactions Microservice | Allister
|  | 9.3 | Add transaction after paypal transaction. | Jeffrey
15 | As a public user, I want to cancel (and refund) a book purchase within 2 hours of ordering an item, so I can change my mind on a product. | 10.1 |  |  |  |  | x | DODs Complete
|  | 10.2 | Transactions Microservice | Allister
|  | 10.3 | Cancel button | Jeffrey
16 | As a registered user, I want to view my transaction history (buy and sell), so I can track my sales and expenses on BOOKEROO. | 18.1 |  |  |  |  | x | DODs Complete
|  | 18.2 | Transactions Microservice: get transactions for one user | Allister
|  | 18.3 | Display transactions for one user. | Mohammed
21 | As a user, I want to see the availability of a book, so that I can know whether or not I can order it. | 19.1 |  |  |  |  | x | DODs Complete
|  | 19.2 | Render availability | Jeffrey