## Sheet1
Sprint 2 UATs
PBI ID | PBI NAME | Meets Expectations | Does Not Meet Expectations | PASS/FAIL | Integration
3 | As an admin, I want to download reports about books, transactions, and other business data in CSV format, so I can conduct stock-take and complete accounting forms.
Criteria 1 | Given that I am the admin And I am on my Dashboard When I click on the reports button And I click on the download report Then the report is downloaded in CSV format | When I click on the link, my transactions table is converted into a csv, and downloaded to my browser. | Non-functional: csv is not very pretty but it does the job | PASS | Frontend uses react-csv library, taking api data and outputting into a csv.
PBI ID | PBI NAME | Meets Expectations | Does Not Meet Expectations | PASS/FAIL | Integration
7 | As an admin user, I want to view a summary of all past and current transactions (sorted by date), so I can keep track of business profits.
Criteria 1 | Given that I am an admin on the admin portal And I want to review BOOKEROO's profits When the summary tab is opened Then I can view a table of all past and current transactions | When navigate to the transactions page in my dashboard, I can see a table of all transactions | Non-functional: table is not very pretty but it does the job | PASS | Frontend send get HTTP request to backend for all transactions.
PBI ID | PBI NAME | Meets Expectations | Does Not Meet Expectations | PASS/FAIL | Integration
11 | As a public user, I want to review books that I have purchased, so I can give my thoughts and opinions on that book.
Criteria 1 | Given that I am a user And that I am on a book's page When I write a review on the book Then my thoughts about the book are broadcast to the public. | The book page has a reviews form where I can enter my content. When I click on post, and refresh the page, my review is displayed. |  | PASS | Frontend sends HTTP post request with the review data. Data is saved to the backend.
Criteria 2 | Given that I am a user And that I am on a book's page When I scroll through the book details Then I see reviews of other readers so I can decide if I want to buy the book | The book page displays all reviews from myself and other people on the book. Each review has a star rating, and the average rating is also displayed. |  | PASS | Frontend sends HTTP get request for this book to get all reviews tied to the book.
PBI ID | PBI NAME | Meets Expectations | Does Not Meet Expectations | PASS/FAIL | Integration
12 | As a business owner, I want to create listings for my books, so that other users can purchase those items.
Criteria 1 | Given that I am a business owner And I am on the business owner Dashboard Page When I click on he sell button And upload the image And upload the table of contents Then the books is listed under books page | The sell books section of the dashboard allows you to choose a book, set a price, and create a listing. |  | PASS | Set of books are returned from the books_ms. We then post HTTP request the listing to the backend.
Criteria 2 | Given I am a user And I am on a book's page, When I scroll through the details Then I can see a list of all listings for this book And decide which to buy from | Each book's page has a list of listings to choose from. It displays the condition price and seller as well as an addtocart button. |  | PASS | We use a HTTP request get to find all listings matching the current book
PASS
PBI ID | PBI NAME | Meets Expectations | Does Not Meet Expectations | PASS/FAIL | Integration
13 | As a public user, I want to create share listings for my books, so that I can provide others with books I don't need.
Criteria 1 | Given that I am a public user And I am on my Dashboard When create a listing for my book Then the book is put up for sale | The sell books section of the dashboard allows you to choose a book, set a price, and create a listing. | Nonfunctional: Share listings are treated the same as normal listings but for 0 dollars. Little bit confusing. | PASS | Same as with the business owner, we post a listing with relevant info from the frontend to the listings_ms using HTTP requests.
PBI ID | PBI NAME | Meets Expectations | Does Not Meet Expectations | PASS/FAIL | Integration
14 | As a public user, I want to pay for transactions using PayPal, so I can have the book delivered to me.
Criteria 1 | Given that I am a customer and I am on the page for finalising an order When I press the checkout button Then I am presented with a paypal window And my transaction is complete if I pay. | I am shown my checkout cart. Paypal allows me to pay for the items. After I pay, my transaction is stored. I can view this in my dashboard. |  | PASS | After the payment, the items in the cart are used to make transactions which are posted to the transactions_ms using a HTTP post request.
PASS
PBI ID | PBI NAME | Meets Expectations | Does Not Meet Expectations | PASS/FAIL | Integration
15 | As a public user, I want to cancel (and refund) a book purchase within 2 hours of ordering an item, so I can change my mind on a product.
Criteria 1 | Given that I am a customer And I have made an unsatisfactory purchase within 2 hours When I make a cancel request Then my order is cancelled And this status is displayed to me | I can cancel my order if it is less than 2 hours. Clicking on the cancel button updates the transaction from "shipping" to "cancelled" |  | PASS | We use a HTTP get request to get a list of transactions including the time that they were created. We use this time to determine whether 2 hours has passed. We use a HTTP post request to update the order as cancelled.
PBI ID | PBI NAME | Meets Expectations | Does Not Meet Expectations | PASS/FAIL | Integration
16 | As a registered user, I want to view my transaction history (buy and sell), so I can track my sales and expenses on BOOKEROO. |  |  | PASS
Criteria 1 | Given that I am a registered user, and I have made purchases, When I visit my dashboard And click on transaction history/orders Then I can keep track of my past purchases | On the dashboard, I can view all the transactions that I have paid for, as transactions where I am the seller. |  | PASS | We use a HTTP get request to get a list of transactions and render them in the frontend
Criteria 2 | Given that I am a business user, And I have been selling books, When I visit my dashboard And click on transaction history Then so I can keep track of my past sales | On the dashboard, I can view all the transactions transactions where I am the seller. |  |  | Same as above.
PBI ID | PBI NAME | Meets Expectations | Does Not Meet Expectations | PASS/FAIL | Integration
21 | As a user, I want to see the availability of a book, so that I can know whether or not I can order it.
Criteria 1 | Given that I am viewing a books listing, When the book is no longer available, Then book's availability will show as no listings. | On the book's page, if there are no listings, a message is displayed saying that no listings are available for that book. |  | PASS | Http get request to get all listings, and render the message if returns zero listings.
PBI ID | PBI NAME | Meets Expectations | Does Not Meet Expectations | PASS/FAIL | Integration