## Sheet1
Sprint 1 Backlog
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
1 | As an unregistered user, I want to signup with my details, so I can create a public or business account with BOOKEROO. | 1.1 |  |  |  |  | x | DODs Complete
|  | 1.2 | Users microservice backend | Allister
|  | 1.3 | Registration form | Jeffrey
2 | As a registered user, I want to enter my login information, so I can be directed to my application dashboard. | 2.1 |  |  |  |  | x | DODs Complete
|  | 2.2 | Login form | Jeffrey
|  | 2.3 | API authentication | Allister
4 | As an admin user, I want to approve/reject business accounts via my portal, so I can verify the legitimacy of a shop owner/publisher. | 4.1 |  |  |  |  | x | DODs Complete
|  | 4.2 | Admin dashboard - Business account requests | Mohammed
|  | 4.3 | API request for 'pending' accounts | Allister
5 | As an admin user, I want power to add/remove/edit users, so I can control account access on the platform. | 5.1 |  |  |  |  | x | DODs Complete
|  | 5.2 | Admin dashboard - All accounts management | Mohammed
|  | 5.3 | API for Users CRUD | Allister
6 | As an admin user, I want to add/remove/edit books, so I can control what information or listings are available to the public. | 6.1 |  |  |  |  | x | DODs Complete
|  | 6.2 | Admin dashboard - All books management | Mohammed
|  | 6.3 | API for Books CRUD | Allister
8 | As a customer, I want to see a book cover image preview with a table of contents, so that I can make an informed decision before buying an item. | 8.1 |  |  |  |  | x | DODs Complete
|  | 8.2 | Book info page | Jeffrey
|  | 8.3 | API call for specific book resource | Ross
9 | As public user, I want to search for books by name, author, ISBN and category, so I can view listings for books based on my interest. | 9.1 |  |  |  |  | x | DODs Complete
|  | 9.2 | Search functionality frontend | Jeffrey
|  | 9.3 | API for GET books with specified params | Ross
10 | As any user, I want to see a list of all available books on the homepage, so I can browse the website's collection. | 10.1 |  |  |  |  | x | DODs Complete
|  | 10.2 | Homepage frontend | Jeffrey
|  | 10.3 | API for GET all books | Ross
18 | As a public user, i want to contact the administrator so that i can contact about them and send a message to them | 18.1 |  |  |  |  | x | DODs Complete
|  | 18.2 | Contact page | Mohammed
|  | 18.3 | Send email to admin | Mohammed
19 | As a public user, I want to view the about page, to know more about the application and its owners | 19.1 |  |  |  |  | x | DODs Complete
|  | 19.2 | About page | Mohammed
22 | As public user, I want to sort book lists by price + other parameters, so I can easily find the books I am looking for. | 22.1 |  |  |  |  | x | DODs Complete
|  | 22.2 | Sort buttons frontend | Jeffrey
|  | 22.3 | Sorting using frontend code | Jeffrey
24 | As a public user, I want to add a listing to my cart, so I can purchase the book later. | 24.1 |  |  |  |  | x | DODs Complete
|  | 24.2 | Front end buttons | Jeffrey
|  | 24.3 | Storing cart items in front end | Jeffrey
25 | As a public user, I want to view and edit my shopping cart, so I can preview the items I will to buy. | 25.1 |  |  |  |  | x | DODs Complete
|  | 25.2 | Front end cart page | Jeffrey
|  | 25.3 | Remove items logic in front end | Jeffrey